## Kaleem
Project Name | Project Feature | ServerIP | File | Folder | Status | Action | Goal | Table Accessed (DB) | Table Altered (DB) | Comment | Date Created | Date Updated
SCIP | Dynamic Dashboard |  | routes.php | app | Altered | _Added lines 9:18 --> paths to new pages | Guiding the way to the populating functions | false | false | moved to live
SCIP
SCIP
SCIP
SCIP
SCIP
SCIP
SCIP
SCIP
SCIP
SCIP
SCIP
| Dynamic Dashboard |  | create.blade.php | app/view/farmergroups | Altered | _Altered lines 100,102 | Change the name of the label for the cooperatives legal document upload Made it possible to upload multiple files at the sale time instead of only one |  |  | Pending to be moved on live
| Dynamic Dashboard |  | edit.blade.php | app/view/farmergroups | Altered | _Altered lines 120:135 | Change the name of the label for the cooperatives legal document upload Made it possible to upload multiple files at the sale time instead of only one Added a button to delete any chosen file |  |  | Pending to be moved on live
| Dynamic Dashboard |  | farmergroupscontroller.php | app/controllers | Altered | _Altered lines 75:107, 44:57, 68,122:141 | Put the files into the correct folder Update the database with the new information |  |  | Pending to be moved on live
| Dynamic Dashboard |  | pagescontroller.php | app/controllers | Altered | _Added lines 202:216 | Find the correct file to download and download it Find the correct file to delete and delete it |  |  | Pending to be moved on live
| Dynamic Dashboard |  | routes.php | app | Altered | _Added lines 73,74 | Point the request to the correct file and or action |  |  | Pending to be moved on live
| Dynamic Dashboard |  | MapController.php | app/controllers | Altered | _Added lines 410:439 | Make the data available on the map relative to the user's permissions | true | false | The security trimming function needs you to join your table with a bunch of other ones ->If your sql query didn't use any select function then you may need to use one to evade any ambiguity between the field -moved on live
| Dynamic Dashboard |  | CooperativesSurveyed.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | CooperativesMapped.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | CooperativesRegistered.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | TotalAreaPlanted.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | TotalAreaAlloted.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | SocialInfrastructurePoints.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | ActiveEnumerators.blade.php | app/view/dashboard | Altered | _Added a search bar | Create a search bar to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativessurveyed.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativesmapped.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativesregistered.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | totalareaplanted.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | totalareaalloted.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | socialinfrastructurepoints.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | activeenumerators.js | public/js | Created |  | Link the search bar to the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | PopUpController.php | app/controllers | Altered | _Added functions to fill the filter's combo boxes based on the page | Send the data for filters and the tables | true | false | Pending to be moved on live
| Loading Function |  | FarmersSurveyed.blade.php | app/view/dashboard | Altered | _added lines 126-130, added ng-cloak in the line no 133 & 236 to hide page flikering, added lines 268,269 for jQuery | Page loader Ajax | false | false | Pending to be moved on live
| Loading Function |  | ofis.admin.css | public/css | Altered | _added lines from 170-185 | bootstrap animation for page loader | false | false | Pending to be moved on live

## Senthil
Project Name | Project Feature | ServerIP | File | Folder | Status | Action | Goal | Table Accessed (DB) | Table Altered (DB) | Comment | Date Created | Date Updated
SCIP | Dynamic Dashboard |  | routes.php | app | Altered | _Added lines 9:18 --> paths to new pages | Guiding the way to the populating functions | false | false | moved to live
| Dynamic Dashboard |  | create.blade.php | app/view/farmergroups | Altered | _Altered lines 100,102 | Change the name of the label for the cooperatives legal document upload Made it possible to upload multiple files at the sale time instead of only one |  |  | Pending to be moved on live
| Dynamic Dashboard |  | edit.blade.php | app/view/farmergroups | Altered | _Altered lines 120:135 | Change the name of the label for the cooperatives legal document upload Made it possible to upload multiple files at the sale time instead of only one Added a button to delete any chosen file |  |  | Pending to be moved on live
| Dynamic Dashboard |  | farmergroupscontroller.php | app/controllers | Altered | _Altered lines 75:107, 44:57, 68,122:141 | Put the files into the correct folder Update the database with the new information |  |  | Pending to be moved on live
| Dynamic Dashboard |  | pagescontroller.php | app/controllers | Altered | _Added lines 202:216 | Find the correct file to download and download it Find the correct file to delete and delete it |  |  | Pending to be moved on live
| Dynamic Dashboard |  | routes.php | app | Altered | _Added lines 73,74 | Point the request to the correct file and or action |  |  | Pending to be moved on live
| Dynamic Dashboard |  | MapController.php | app/controllers | Altered | _Added lines 410:439 | Make the data available on the map relative to the user's permissions | true | false | The security trimming function needs you to join your table with a bunch of other ones ->If your sql query didn't use any select function then you may need to use one to evade any ambiguity between the field -moved on live
| Dynamic Dashboard |  | CooperativesSurveyed.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | CooperativesMapped.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | CooperativesRegistered.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | TotalAreaPlanted.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | TotalAreaAlloted.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | SocialInfrastructurePoints.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | ActiveEnumerators.blade.php | app/view/dashboard | Altered | _Added a search bar | Create a search bar to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativessurveyed.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativesmapped.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativesregistered.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | totalareaplanted.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | totalareaalloted.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | socialinfrastructurepoints.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | activeenumerators.js | public/js | Created |  | Link the search bar to the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | PopUpController.php | app/controllers | Altered | _Added functions to fill the filter's combo boxes based on the page | Send the data for filters and the tables | true | false | Pending to be moved on live
| Loading Function |  | FarmersSurveyed.blade.php | app/view/dashboard | Altered | _added lines 126-130, added ng-cloak in the line no 133 & 236 to hide page flikering, added lines 268,269 for jQuery | Page loader Ajax | false | false | Pending to be moved on live
| Loading Function |  | ofis.admin.css | public/css | Altered | _added lines from 170-185 | bootstrap animation for page loader | false | false | Pending to be moved on live

## Jonathan
Project Name | Project Feature | ServerIP | File | Folder | Status | Action | Goal | Table Accessed (DB) | Table Altered (DB) | Comment | Date Created | Date Updated
SCIP | Dynamic Dashboard |  | routes.php | app | Altered | _Added lines 9:18 --> paths to new pages | Guiding the way to the populating functions | false | false | moved to live
| Dynamic Dashboard |  | create.blade.php | app/view/farmergroups | Altered | _Altered lines 100,102 | Change the name of the label for the cooperatives legal document upload Made it possible to upload multiple files at the sale time instead of only one |  |  | Pending to be moved on live
| Dynamic Dashboard |  | edit.blade.php | app/view/farmergroups | Altered | _Altered lines 120:135 | Change the name of the label for the cooperatives legal document upload Made it possible to upload multiple files at the sale time instead of only one Added a button to delete any chosen file |  |  | Pending to be moved on live
| Dynamic Dashboard |  | farmergroupscontroller.php | app/controllers | Altered | _Altered lines 75:107, 44:57, 68,122:141 | Put the files into the correct folder Update the database with the new information |  |  | Pending to be moved on live
| Dynamic Dashboard |  | pagescontroller.php | app/controllers | Altered | _Added lines 202:216 | Find the correct file to download and download it Find the correct file to delete and delete it |  |  | Pending to be moved on live
| Dynamic Dashboard |  | routes.php | app | Altered | _Added lines 73,74 | Point the request to the correct file and or action |  |  | Pending to be moved on live
| Dynamic Dashboard |  | MapController.php | app/controllers | Altered | _Added lines 410:439 | Make the data available on the map relative to the user's permissions | true | false | The security trimming function needs you to join your table with a bunch of other ones ->If your sql query didn't use any select function then you may need to use one to evade any ambiguity between the field -moved on live
| Dynamic Dashboard |  | CooperativesSurveyed.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | CooperativesMapped.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | CooperativesRegistered.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | TotalAreaPlanted.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | TotalAreaAlloted.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | SocialInfrastructurePoints.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | ActiveEnumerators.blade.php | app/view/dashboard | Altered | _Added a search bar | Create a search bar to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativessurveyed.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativesmapped.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativesregistered.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | totalareaplanted.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | totalareaalloted.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | socialinfrastructurepoints.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | activeenumerators.js | public/js | Created |  | Link the search bar to the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | PopUpController.php | app/controllers | Altered | _Added functions to fill the filter's combo boxes based on the page | Send the data for filters and the tables | true | false | Pending to be moved on live
| Loading Function |  | FarmersSurveyed.blade.php | app/view/dashboard | Altered | _added lines 126-130, added ng-cloak in the line no 133 & 236 to hide page flikering, added lines 268,269 for jQuery | Page loader Ajax | false | false | Pending to be moved on live
| Loading Function |  | ofis.admin.css | public/css | Altered | _added lines from 170-185 | bootstrap animation for page loader | false | false | Pending to be moved on live

## Loic
Project Name | Project Feature | ServerIP | File | Folder | Status | Action | Goal | Table Accessed (DB) | Table Altered (DB) | Comment | Date Created | Date Updated
SCIP | Dynamic Dashboard |  | routes.php | app | Altered | _Added lines 9:18 --> paths to new pages | Guiding the way to the populating functions | false | false | moved to live
| Dynamic Dashboard |  | create.blade.php | app/view/farmergroups | Altered | _Altered lines 100,102 | Change the name of the label for the cooperatives legal document upload Made it possible to upload multiple files at the sale time instead of only one |  |  | Pending to be moved on live
| Dynamic Dashboard |  | edit.blade.php | app/view/farmergroups | Altered | _Altered lines 120:135 | Change the name of the label for the cooperatives legal document upload Made it possible to upload multiple files at the sale time instead of only one Added a button to delete any chosen file |  |  | Pending to be moved on live
| Dynamic Dashboard |  | farmergroupscontroller.php | app/controllers | Altered | _Altered lines 75:107, 44:57, 68,122:141 | Put the files into the correct folder Update the database with the new information |  |  | Pending to be moved on live
| Dynamic Dashboard |  | pagescontroller.php | app/controllers | Altered | _Added lines 202:216 | Find the correct file to download and download it Find the correct file to delete and delete it |  |  | Pending to be moved on live
| Dynamic Dashboard |  | routes.php | app | Altered | _Added lines 73,74 | Point the request to the correct file and or action |  |  | Pending to be moved on live
| Dynamic Dashboard |  | MapController.php | app/controllers | Altered | _Added lines 410:439 | Make the data available on the map relative to the user's permissions | true | false | The security trimming function needs you to join your table with a bunch of other ones ->If your sql query didn't use any select function then you may need to use one to evade any ambiguity between the field -moved on live
| Dynamic Dashboard |  | CooperativesSurveyed.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | CooperativesMapped.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | CooperativesRegistered.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | TotalAreaPlanted.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | TotalAreaAlloted.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | SocialInfrastructurePoints.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | ActiveEnumerators.blade.php | app/view/dashboard | Altered | _Added a search bar | Create a search bar to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativessurveyed.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativesmapped.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativesregistered.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | totalareaplanted.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | totalareaalloted.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | socialinfrastructurepoints.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | activeenumerators.js | public/js | Created |  | Link the search bar to the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | PopUpController.php | app/controllers | Altered | _Added functions to fill the filter's combo boxes based on the page | Send the data for filters and the tables | true | false | Pending to be moved on live
| Loading Function |  | FarmersSurveyed.blade.php | app/view/dashboard | Altered | _added lines 126-130, added ng-cloak in the line no 133 & 236 to hide page flikering, added lines 268,269 for jQuery | Page loader Ajax | false | false | Pending to be moved on live
| Loading Function |  | ofis.admin.css | public/css | Altered | _added lines from 170-185 | bootstrap animation for page loader | false | false | Pending to be moved on live

## Bertrand
Project Name | Project Feature | ServerIP | File | Folder | Status | Action | Goal | Table Accessed (DB) | Table Altered (DB) | Comment | Date Created | Date Updated
SCIP | Dynamic Dashboard |  | routes.php | app | Altered | _Added lines 9:18 --> paths to new pages | Guiding the way to the populating functions | false | false | moved to live
| Dynamic Dashboard |  | create.blade.php | app/view/farmergroups | Altered | _Altered lines 100,102 | Change the name of the label for the cooperatives legal document upload Made it possible to upload multiple files at the sale time instead of only one |  |  | Pending to be moved on live
| Dynamic Dashboard |  | edit.blade.php | app/view/farmergroups | Altered | _Altered lines 120:135 | Change the name of the label for the cooperatives legal document upload Made it possible to upload multiple files at the sale time instead of only one Added a button to delete any chosen file |  |  | Pending to be moved on live
| Dynamic Dashboard |  | farmergroupscontroller.php | app/controllers | Altered | _Altered lines 75:107, 44:57, 68,122:141 | Put the files into the correct folder Update the database with the new information |  |  | Pending to be moved on live
| Dynamic Dashboard |  | pagescontroller.php | app/controllers | Altered | _Added lines 202:216 | Find the correct file to download and download it Find the correct file to delete and delete it |  |  | Pending to be moved on live
| Dynamic Dashboard |  | routes.php | app | Altered | _Added lines 73,74 | Point the request to the correct file and or action |  |  | Pending to be moved on live
| Dynamic Dashboard |  | MapController.php | app/controllers | Altered | _Added lines 410:439 | Make the data available on the map relative to the user's permissions | true | false | The security trimming function needs you to join your table with a bunch of other ones ->If your sql query didn't use any select function then you may need to use one to evade any ambiguity between the field -moved on live
| Dynamic Dashboard |  | CooperativesSurveyed.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | CooperativesMapped.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | CooperativesRegistered.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | TotalAreaPlanted.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | TotalAreaAlloted.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | SocialInfrastructurePoints.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | ActiveEnumerators.blade.php | app/view/dashboard | Altered | _Added a search bar | Create a search bar to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativessurveyed.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativesmapped.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativesregistered.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | totalareaplanted.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | totalareaalloted.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | socialinfrastructurepoints.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | activeenumerators.js | public/js | Created |  | Link the search bar to the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | PopUpController.php | app/controllers | Altered | _Added functions to fill the filter's combo boxes based on the page | Send the data for filters and the tables | true | false | Pending to be moved on live
| Loading Function |  | FarmersSurveyed.blade.php | app/view/dashboard | Altered | _added lines 126-130, added ng-cloak in the line no 133 & 236 to hide page flikering, added lines 268,269 for jQuery | Page loader Ajax | false | false | Pending to be moved on live
| Loading Function |  | ofis.admin.css | public/css | Altered | _added lines from 170-185 | bootstrap animation for page loader | false | false | Pending to be moved on live

## Vignesh
Project Name | Project Feature | ServerIP | File | Folder | Status | Action | Goal | Table Accessed (DB) | Table Altered (DB) | Comment | Date Created | Date Updated
SCIP | Dynamic Dashboard |  | routes.php | app | Altered | _Added lines 9:18 --> paths to new pages | Guiding the way to the populating functions | false | false | moved to live
| Dynamic Dashboard |  | create.blade.php | app/view/farmergroups | Altered | _Altered lines 100,102 | Change the name of the label for the cooperatives legal document upload Made it possible to upload multiple files at the sale time instead of only one |  |  | Pending to be moved on live
| Dynamic Dashboard |  | edit.blade.php | app/view/farmergroups | Altered | _Altered lines 120:135 | Change the name of the label for the cooperatives legal document upload Made it possible to upload multiple files at the sale time instead of only one Added a button to delete any chosen file |  |  | Pending to be moved on live
| Dynamic Dashboard |  | farmergroupscontroller.php | app/controllers | Altered | _Altered lines 75:107, 44:57, 68,122:141 | Put the files into the correct folder Update the database with the new information |  |  | Pending to be moved on live
| Dynamic Dashboard |  | pagescontroller.php | app/controllers | Altered | _Added lines 202:216 | Find the correct file to download and download it Find the correct file to delete and delete it |  |  | Pending to be moved on live
| Dynamic Dashboard |  | routes.php | app | Altered | _Added lines 73,74 | Point the request to the correct file and or action |  |  | Pending to be moved on live
| Dynamic Dashboard |  | MapController.php | app/controllers | Altered | _Added lines 410:439 | Make the data available on the map relative to the user's permissions | true | false | The security trimming function needs you to join your table with a bunch of other ones ->If your sql query didn't use any select function then you may need to use one to evade any ambiguity between the field -moved on live
| Dynamic Dashboard |  | CooperativesSurveyed.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | CooperativesMapped.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | CooperativesRegistered.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | TotalAreaPlanted.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | TotalAreaAlloted.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | SocialInfrastructurePoints.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | ActiveEnumerators.blade.php | app/view/dashboard | Altered | _Added a search bar | Create a search bar to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativessurveyed.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativesmapped.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativesregistered.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | totalareaplanted.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | totalareaalloted.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | socialinfrastructurepoints.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | activeenumerators.js | public/js | Created |  | Link the search bar to the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | PopUpController.php | app/controllers | Altered | _Added functions to fill the filter's combo boxes based on the page | Send the data for filters and the tables | true | false | Pending to be moved on live
| Loading Function |  | FarmersSurveyed.blade.php | app/view/dashboard | Altered | _added lines 126-130, added ng-cloak in the line no 133 & 236 to hide page flikering, added lines 268,269 for jQuery | Page loader Ajax | false | false | Pending to be moved on live
| Loading Function |  | ofis.admin.css | public/css | Altered | _added lines from 170-185 | bootstrap animation for page loader | false | false | Pending to be moved on live

## Darick
Project Name | Project Feature | ServerIP | File | Folder | Status | Action | Goal | Table Accessed (DB) | Table Altered (DB) | Comment | Date Created | Date Created2
SCIP | Dynamic Dashboard |  | routes.php | app | Altered | _Added lines 9:18 --> paths to new pages | Guiding the way to the populating functions | false | false | moved to live
| Dynamic Dashboard |  | create.blade.php | app/view/farmergroups | Altered | _Altered lines 100,102 | Change the name of the label for the cooperatives legal document upload Made it possible to upload multiple files at the sale time instead of only one |  |  | Pending to be moved on live
| Dynamic Dashboard |  | edit.blade.php | app/view/farmergroups | Altered | _Altered lines 120:135 | Change the name of the label for the cooperatives legal document upload Made it possible to upload multiple files at the sale time instead of only one Added a button to delete any chosen file |  |  | Pending to be moved on live
| Dynamic Dashboard |  | farmergroupscontroller.php | app/controllers | Altered | _Altered lines 75:107, 44:57, 68,122:141 | Put the files into the correct folder Update the database with the new information |  |  | Pending to be moved on live
| Dynamic Dashboard |  | pagescontroller.php | app/controllers | Altered | _Added lines 202:216 | Find the correct file to download and download it Find the correct file to delete and delete it |  |  | Pending to be moved on live
| Dynamic Dashboard |  | routes.php | app | Altered | _Added lines 73,74 | Point the request to the correct file and or action |  |  | Pending to be moved on live
| Dynamic Dashboard |  | MapController.php | app/controllers | Altered | _Added lines 410:439 | Make the data available on the map relative to the user's permissions | true | false | The security trimming function needs you to join your table with a bunch of other ones ->If your sql query didn't use any select function then you may need to use one to evade any ambiguity between the field -moved on live
| Dynamic Dashboard |  | CooperativesSurveyed.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | CooperativesMapped.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | CooperativesRegistered.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | TotalAreaPlanted.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | TotalAreaAlloted.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | SocialInfrastructurePoints.blade.php | app/view/dashboard | Altered | _Added a filter menu in the header which appears as a button | Create a filter drop down menu in the header to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | ActiveEnumerators.blade.php | app/view/dashboard | Altered | _Added a search bar | Create a search bar to filter the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativessurveyed.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativesmapped.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | cooperativesregistered.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | totalareaplanted.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | totalareaalloted.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | socialinfrastructurepoints.js | public/js | Created | _Code to make the filter menu work | Activate the filter button and set it's functions | false | false | Pending to be moved on live
| Dynamic Dashboard |  | activeenumerators.js | public/js | Created |  | Link the search bar to the table | false | false | Pending to be moved on live
| Dynamic Dashboard |  | PopUpController.php | app/controllers | Altered | _Added functions to fill the filter's combo boxes based on the page | Send the data for filters and the tables | true | false | Pending to be moved on live
| Loading Function |  | FarmersSurveyed.blade.php | app/view/dashboard | Altered | _added lines 126-130, added ng-cloak in the line no 133 & 236 to hide page flikering, added lines 268,269 for jQuery | Page loader Ajax | false | false | Pending to be moved on live
| Loading Function |  | ofis.admin.css | public/css | Altered | _added lines from 170-185 | bootstrap animation for page loader | false | false | Pending to be moved on live